10th October 2024

Things discussed and action items

- Groups were formed

- Tyrone will get in touch with Amber

- WhatsApp group was formed by Tyrone

- Everyone goes through the assignment and come next week

17th October 2024

Things discussed and action items

- Everyone was present including Amber

- We agreed to divide the tasks

A black background with white text

Description automatically generated

20th October 2024

Things discussed and action items

- Amber informs she is dropping out

24th October 2024

Things discussed and action items

- Everyone has a good idea about the assignment

- Tyrone has done some data cleaning

- Everyone will work on data cleaning

- Chavin agrees to work on finding themes

- Tyrone agrees to work on sentiment analysis

- Josh agrees to work on critical moment analysis.

- Everyone will work on evaluation

26th October 2024

Things discussed and action items

* Chavin is working on cleaning data and finding themes, hoping to finish it by monday
* Tyrone will work on sentiment analysis after themes are found

28th October 2024

Things discussed and action items

* Themes are finislised and viusalised
* Work on the sentiment analysis chavin and Tyrone
* Josh starts looking into Critical moment analysis with the visualisations created

30th October

Things discussed and action items

* Chavin and Tyrone has identified sentiment and sentiment scores and visualised charts for Sentiment Analysis part 1
* Josh continues to work on critical moment analysis with the available charts and visualisations. Also has done some visualisations for critical moment Analysis

1st November

Things discussed and action items

* Chavin and Tyrone is working on the report part
* We all looked Into critical moment analysis

Chavin has created a survery to do the evaluation

3rd November

Things discussed and action items

* Chavin has completed evaluation with tutorial group members through online survey
* Tyrone has finished sentimental analysis
* Josh finalising critical moment analysis and suggesting improvements to all visualisations to make them better
* 4th November

Things discussed and action items

* Everyone completed their individual report by 6pm
* Plan is to complete the whole report by 10pm.